## Issue Description
CR No. | Issue Description | BU | Module | Issue Type | Priority | Severity | Responsible person | Resolution
ERP-2022-0001393 | เมื่อทำการ Revalue Asset แล้ว ไม่มียอดแสดงใน Asset Movement Report | BTSG | AA | Configuration | Low | Low | Ampaporn C. | BA ทำการ Config เพิ่มเติม เนื่องจากโปรแกรม Asset movement Report จะเข้าไปป Submit ข้อมูลจาก Asset History Report Abaper ทำการเพิ่ม Column สำหรับ Revaluation และแก้ไขโปรแกรมให้ไปนำข้อมู] column "BTR17" ที่ Asset history sheet มาแสดงที่ Asset movment Report

## BA Test
UAT Client : | DEV 230
Test by : | Ampaporn C'
No. | Test Case Description | Test Data | Expected Results | Actual Results | Status | Remark
1 | Asset Movement Report T-code : ZAAR007 | Compapny code : 1010 Report year : 2021 Report Period : 1 to 12 | Asset movement Report is correct | - Refer to "Test Result by BA" | Pass
2 | Asset Movement Report T-code : ZAAR007 | Compapny code : 1010 Report year : 2022 Report Period : 1 to 12 | Asset movement Report is correct | - Refer to "Test Result by BA" | Pass
3 | GL Account Line Item Display T-code : FAGLL03 | GL Account : All Account about Fixed Asset Compapny code : 1010 All Item As of : From _____ To 31.03.2023 | Can compare with 1 , 2 | - Refer to "Test Result by BA" | Pass
4 | Check amount with Asset balance report T-code : AR01 | Company code : 1010 Report date : 31.03.2023 | Can compare with 1 , 2 | - Refer to "Test Result by BA" | Pass

## Test Result by BA
Test Result No1
Test Result No2
Test Result No3

## UAT
UAT Client : | QAS 850
Test by :
No. | Test Case Description | Test Data | Expected Results | Actual Results | Status | Remark
1 | Asset Movement Report T-code : ZAAR007 | Compapny code : 1010 Report year : 2021 Report Period : 1 to 12 | Asset movement Report is correct | - Refer to "Test Result by UAT" | Not Started
2 | Asset Movement Report T-code : ZAAR007 | Compapny code : 1010 Report year : 2022 Report Period : 1 to 12 | Asset movement Report is correct | - Refer to "Test Result by UAT" | Not Started
3 | GL Account Line Item Display T-code : FAGLL03 | GL Account : All Account about Fixed Asset Compapny code : 1010 All Item As of : From _____ To 31.03.2023 | Can compare with 1 , 2 | - Refer to "Test Result by UAT" | Not Started
4 | Check amount with Asset balance report T-code : AR01 | Company code : 1010 Report date : 31.03.2023 | Can compare with 1 , 2 | - Refer to "Test Result by UAT" | Not Started

## GL (hidden)
Module | Single Role | Role Description
GL | Z:GL_D_GL_Master_5050 | Display GL Master 5050
GL | Z:GL_D_Exchange_Rate_0000 | Display Exchange Rate 0000
GL | Z:GL_D_Open_Close_Period_5050 | Display Period 5050
GL | Z:GL_M_Park_Document_5050 | Parked Document 5050
GL | Z:GL_M_Post_with_Clearing_5050 | Post with Clearing, Account Clear 5050
GL | Z:GL_M_Recurring_Document_5050 | Create, Change Recurring Document 5050
GL | Z:GL_M_Accrual_Object_5050 | Create, Change Accrual Object 5050
GL | Z:GL_M_Accrual_Document_5050 | Post Accrual/Deferral Document, Reverse Accrual/Deferral Document 5050
GL | Z:GL_M_Edit_Parked_Doc_5050 | Change Parked Document 5050
GL | Z:GL_M_Edit_Posted_Doc_5050 | Change Posted Document 5050
GL | Z:GL_M_Automatic_Clearing_5050 | Post Automatic Clearing 5050
GL | Z:GL_M_Reclassify_5050 | Post Reclassify Document 5050
GL | Z:GL_M_Revaluation_5050 | Post Revaluation Document 5050
GL | Z:GL_D_Parked_Document_5050 | Display Parked Document 5050
GL | Z:GL_D_FI_Document_5050 | Display Document 5050
GL | Z:GL_D_GL_Common_Rpt_5050 | Display GL Line Item, GL Balance 5050
GL | Z:GL_D_GL_Report_5050 | Display General Report 5050